## Sheet1
Risk Mitigation, Monitoring and Management Plan
Name | Category | Probability | Impact | Description | Monitoring | Proactive Actions | Reactive Actions
Loss of personnel | Project | Low | High | One or more team members decide to leave the team. | Monitor team members to see if they seem likely to leave. | Get a couple of week early notice from the team member before he/she leaves. | Reassign tasks to the available team members, and inform the manager of the loss of the team member.
Miscommunication with the client | Project | Low | High | Miss understanding that clients requirments can ocurr as project goes on. | Always check with the client whether the project is meeting their needs and if they are happy with what has been developed already. | During the protypes demonstration with the client, check with client if everything is on track. | Find out what has been misunderstood and re-plan to meet the client needs.
Authentication system fails or has flaws. | Technical | Low | High | Design flaws in the system allows for unauthorized access to the system | Do a regular check, testing differenent components of the authenticaiton system | Adopt the Google authentication system, since it is a more reliable system. | Assign a team member or two to develop our own version of the authentication system.
Project goes over time | Business | Low | Medium | A possibility is that the team doesn’t manage to finish the project on time, can happen as a result of lack of preparation. | Develop a Gantt chart that has set milestones and decision points at critical stages which will help us identify our progress | Keep modifying and updating the Gantt chart so that it meets the deadline. | Renegotiate deadline with the client, explaining why that is the case.
Problems with technology (Google App Engine) | Technical | Medium | Medium | We will be using some new technologies and there is the possibility that we struggle and don’t mange to learn the new tech. | Team leader to continuously check with team members and see how comfortable they are with the technology, and if they aren’t, find out what’s bothering them and help them to manage it. | Before choosing the technology make sure that team member are confident in using the technology and they have no problem learning it. Also have a plan B, i.e. another technology that can be used (Java) | Find out the problems that are faced and try and solve them, otherwise change the technology to a java development environment.
End product has usability issues | Technical | Low | Medium | User find it hard to understand the GUI, and find it hard to navigate the website | Adopt good HCI practices | Test the GUI before the final deployment. Tests must include a wide range of users (novice and expert). | Understand the difficulties the user is facing and modify the GUI in accordance to that
Project requirements change | Project | Medium | Medium | Client changes the requirements sometime during development | Regularly check progress against Requirements. | Try and maintain regular communication with the client. | Check if the new requirements require re planning and reassigning tasks to the team.
Deviation from software engineering standards | Technical | Low | Medium | With the progress of the develpoment it is possible to lose track and start deviating from the common and known software engineering standards | All relevant documents must be complete and as accurate as possible to ensure they conform with common software enigneering standards | Tehnical reviews to be done during major milestones to ensure that the project is in line with established software engineering standards | steps must be taken back as soon as the deviations are spotted, and try and guide and the project back to meet the standards.
Loss of data | Project | Low | Medium | While team member are working on their own copy of the applciation, they might encounter loss of data | be as complete and accurate as possible to ensure that work will conform to | Once you have a working copy, commit to the repositry | Get the team member who was working on that lost data to start re-developing whats lost immediatly, assign another team member if help is needed.
Standards | Staff | Medium | Medium | Team members fail to communicate with each other | expressed software engineering standards | Get regular feedback from members to see if there are problems. | Find out what’s wrong, try and solve the problem, if couldn’t solve the issue, split the team into two teams.
Lack of team Knowledge | Staff | High | Low | The team might lack someone who specializes in a particular field. | Team leader to know the team very well and know their relative experiences | Before the implementation phase check whether the team has the knowledge to accomplish all the given tasks | Seek knowledge, assign task to a member and the member needs to learn what’s needed to accomplish the task.